## Project Plan
# | Risk ID | Title | Description | Raised By | Raised On | Impact | Probability | Criticality | Status | Mitigation Action | Owner | Due Date | Comments | Attachments | Log Type | Escalation to Riddell LT | Escalation to Steerco | Delivery Module | Delivery Type
1 | R-0001 | Provisioning strategies delays | Delays in alignment on provisioning strategies will impact the start of critical milestones. | Jon Hall | 11-11-2025 | High (0.70) | Medium (0.50) | Medium | In progress | Discussion set for 12/9 to confirm bast practice landscape. 1/6/26: Thanges to reconcile available DEV clients and communicate any additional clientsneeded ; then to socialize with the team. | Thangeswaran TK | 12-01-2026 | Not seeing QA client as a barrier with client copy opportunity. (Posted by Jonathan Hall, Nov 21, 2025) 12/8 - Misalignment between landscape expectations are delaying provisioning. Thangesh organizing a session on best practices. (Posted by Jonathan Hall, Dec 11, 2025)
2 | R-0006 | Simbex FY alignment | Simbex operates as a separate legal entity within the Riddell group, but it follows a distinct fiscal year variant and posting period configuration. | Dilli | 11-11-2025 | High (0.70) | Medium (0.50) | Medium | Completed | We won't be bring SImbex forward in our S/4 program. | Dillibabu Teegala | 21-11-2025
3 | R-0005 | Onshore / Offshore handshake | Must ensure the offshore team is ready to engage the project in the short term. | Aravind | 11-11-2025 | High (0.70) | Medium (0.50) | High | Completed | Onsite visit set to confirm engagement is satisfactory (Dec-16). | Santosh Prakash | 16-12-2025 | Resource must be familiar with Riddell processes. Must be fully enabled of tools, templates, plans. (Posted by Jonathan Hall, Nov 21, 2025) Feedback from visit was positive. "Overall, it was an extremely positive and productive visit. We had strong interactions with each of the STRIDE team members and came away with a high degree of confidence in the team’s ability to successfully deliver the STRIDE program. The depth of engagement, clarity of thought, and professionalism demonstrated by the team were evident throughout our discussions." Closing item. (Posted by Jonathan Hall, Dec 18, 2025)
4 | R-0004 | Advanced Variant Configurator | Delay in design finalization will impact closure of Explorer phase and impact sales BOM timing for Riddell | Nafis | 11-11-2025 | Medium (0.50) | Medium (0.50) | Medium | Completed | Awaiting closure answer from SAP. 1/6/26: Aligned that path is sufficient. | Nafis Pathan | 17-12-2025 | Aligned to move forward with AVC. Not moving Hybris B2B to Commerce Cloud; confirmed integration between Hybris and S/4 via AVC not a barrier. (Posted by Jonathan Hall, Nov 21, 2025)
5 | R-0002 | OpenText VIM scope change | OT implementations could require a significant timeline that requires proper alignment with S/4 milestones. Inclusion of OT VIM into scope could significantly challenge S/4 commitments. | Jon Hall | 11-11-2025 | Medium (0.50) | High (0.70) | Medium | Completed | Acquire detailed SOW of implementation services. Must manage level of customization during requirements gathering. 1/6/26: Decision taken to move forward with Vital | Jonathan Hall | 19-12-2025
6 | R-0003 | RFID Serialization | Indecision on design could delay Explore phase exit/sign-off. | Jon Hall | 11-11-2025 | Medium (0.50) | Medium (0.50) | Medium | Completed | Aditya researching and reviewing whether he can capture all data in a custom table (custom). | Aditya Gajula | 01-12-2025 | Decision - not going forward with SAP proposed functionality. (Posted by Jonathan Hall, Nov 21, 2025)
7 | R-0007 | Explore Phase delay (Func/Tech) | Incomplete Fit-to-Gap anaylsis / process flows are contributing to expected delays. | Nafis | 21-11-2025 | High (0.70) | High (0.70) | High | Completed | Granular true-up provided on Dec-3 to establish single source of truth for full transparency and tracking. | Jonathan Hall | 15-12-2025 | Awaiting plan true-up acceptance at SteerCo to close. (Posted by Jonathan Hall, Dec 8, 2025)
8 | R-0010 | Significant customization | Significant WRICEF inventory impacts timeline & Greenfield vision. Initial numbers indicate 3x desired customizations. | Jon Hall | 10-12-2025 | High (0.70) | High (0.70) | High | In progress | SSB board approval will establish closure. | Thangeswaran TK | 23-01-2026 | Expectation that all customizations must be vetted (CoE included). (Posted by Jonathan Hall, Jan 14, 2026)
9 | R-0008 | Finance Resource to support critical path | Suppressed critical path for Finance is supported by the onboarding of a productive FI resource by Jan-5 (with 10 day buffer). | Jon Hall | 10-12-2025 | High (0.70) | Medium (0.50) | Medium | Completed | Ravi Karnati has been allocated to assist. Vamshi also allocated. | Jonathan Hall | 05-01-2026 | Ravi has also joined in addition to Vamshi (offshore). (Posted by Jonathan Hall, Jan 14, 2026)
10 | R-0009 | GSI Inventory not yet stable | Bringing in additional GSIs at this stage increases scope and impacts resource capacity and schedule. | Jon Hall | 10-12-2025 | High (0.70) | High (0.70) | High | In progress | Consensus reached that GSIs are stable. Will issue KTERN approval. | Nallam Paramkousam | 09-01-2026
11 | R-0012 | Recruitment of MM Consultant | Recruitment of MM Consultant | Santosh Prakash | 16-12-2025 |  |  | High | Completed | Discussion done along with PARAM & RMG. RMG working on it. |  | 31-12-2025
12 | R-0013 | Recruitment of Fashion Consultant | Recruitment of Fashion Consultant | Santosh Prakash | 16-12-2025 | Medium (0.50) | Medium (0.50) | High | In progress | Discussion done along with PARAM & RMG. RMG working on it. |  | 16-01-2026
13 | R-0014 | Recruitment of Onsite CSM | Recruitment of Onsite CSM | Santosh Prakash | 16-12-2025 |  |  | High | Completed | Discussion done along with PARAM & RMG. RMG working on it. |  | 31-12-2025
14 | R-0015 | Recruitment of Data Migration Consultant | Recruitment of Data Migration Consultant | Santosh Prakash | 16-12-2025 |  |  | High | Completed | 2 DM hires completed. | Jonathan Hall | 12-01-2026
15 | R-0011 | Lack of dependencies in the KTERN project plan | Lack of dependencies introduce a lack of transparency. | Caleb Green | 24-12-2025 | Medium (0.50) | Medium (0.50) | Medium | In progress | Dependency functionality realized at activity level; request poojitha to apply to critical path. | Jonathan Hall | 23-01-2026
16 | R-0018 | Analytics scope creep due to any legacy BW expectations | Efforts to recreate any BW Bex queries or KPI logics may result in re-implementation of BW 2.0 in Datasphere. Priority should be S/4 HANA embedded analytics and only true gaps, history developed in Datasphere SAC | Sathya | 23-12-2025 | Medium (0.50) | Medium (0.50) | Medium | In progress | Call meeting to review process to ensure WRICEF process is included properly. | Jonathan Hall | 16-01-2026 | Data wise, ECC data is the source. COnclude report list with Getty. (Posted by Jonathan Hall, Jan 7, 2026)
17 | R-0019 | High complexity from Unified BW Historical and S/4 Operational Models | Selection of unified historical + operational analytics may introduce significant semantic, reconciliation and design complexity. | Sathya | 23-12-2025 | High (0.70) | High (0.70) | High | New | Treat unification as high-risk exception. Rebaseline scope, timeline | Jonathan Hall | 13-01-2026 | Jo to setup session with Sathya. (Posted by Jonathan Hall, Jan 7, 2026)